## Sheet1
Priority | Sprint | To Do List | Status
Required | 1 | To set-up Git-Hub project | Done
Required | 1 | To get project to build to self-contained JAR with Maven | Attempted
Required | 1 | To set-up working Dockerfile for project | Attempted
Required | 1 | Travis CI for project is set-up and build is working using JAR and Docker on Travis CI | Attempted
Required | 1 | Correct branches for GitFlow workflow are created - includes master, develop, and release branches | Done
Required | 1 | First release created on GitHub | Done
Required | 1 | To define code of conduct | Done
Required | 2 | Issues being used on GitHub | Not Attempted
Required | 2 | Tasks defined as user stories | Not Attempted
Required | 2 | Project integrated with Zube.io | Not Attempted
Required | 2 | Kanban/Project Board being used | Not Attempted
Required | 2 | Sprint Boards being used | Not Attempted
Required | 2 | Full use cases defined | Not Attempted
Required | 3 | Suitable unit tests defined | Not Attempted
Required | 3 | Suitable intergration tests efined | Not Attempted
Required | 3 | Tests running on Travis CI | Not Attempted
Required | 4 | Deployment working | Not Attempted
Required | 4 | Bug reporting system set-up | Not Attempted